## Phase 2
SCION Phase 2 — Unified Delivery Plan
1 developer + AI-assisted (Claude Code) ¦ ~39 net days ¦ ~4 weeks ¦ Revised: 2026-07-17
# | Item | Description | Days | Notes
FOUNDATION — Database migration + performance
1 | SQLite → Postgres | DB engine migration — performance foundation | 4 | Enables items 2–4 at scale
↳ 1a | Graph engine perf | Lazy-load nodes + indexing | 2 | Sub-task of 1
↳ 1b | Frontend pagination | Server-side pagination + lazy graph fetch | 2 | Sub-task of 1
ARCHITECTURE LAYERS — Staging → Integration → Access (Jon Brightling, 2026-07-17)
2 | Staging Layer | Validation + cross-source conflict resolution | 5 | Prerequisite of item 3
3 | Integration Model | Persistent entity layer + backfill + trend UI | 7 | Requires item 2
4 | Access Layer | Business Discovery + Exec Dashboard + Entity view | 4 | Requires items 3 + 8
ADDITIONAL SCOPE — Remaining Phase 2 items
5 | Production runtime | Systemd units + structured JSON logging | 1
6 | Col-lineage navigation | Interactive downstream + upstream traversal | 5
7 | AI column classification | PII / non-PII by name, data type and comment | 3
8 | Reference data | User hierarchy + app metadata + new dashboards | 5 | Blocked: extractor change
9 | Incremental loading | CDC against day-zero baseline | 4
10 | Manifest timestamps | Extractor timestamps on snapshot screen | 1
11 | Buffer (contingency) | Reserved for unanticipated high-priority items | 5
Gross total (excl. sub-items) |  |  | 49 days
AI-assisted gain (~20%) |  |  | 10 days
Net total |  |  | ~39 days | ~6 weeks
• NOTE: Item 8 (Reference data) is blocked until the extractor provides one row per username (today: aggregated user_count only).
• NOTE: Item 2 (Staging Layer) is a prerequisite for item 3 (Integration Model). Item 4 (Access Layer) requires items 3 + 8.
• NOTE: Item 1 (SQLite→Postgres) was previously conditional — promoted to first item as the performance foundation needed before building the Integration Model at scale.
• NOTE: Sub-tasks 1a + 1b (4 days) are part of item 1 and not double-counted in the gross or net totals.

## Summary
SCION Phase 2 — Estimate Summary
Estimate date | 2026-07-17 (revised post-Pilar meeting)
Original estimate | 2 weeks (pre-Meeting 28 scope)
Meeting 28 estimate | 2 weeks — Delivery 1 committed
Revised estimate | ~4 weeks — single delivery (all scope)
Developer | Guillermo Albella + Claude Code (AI-assisted)
Estimate to Rahul | Monday 2026-07-21
Presentation | Thursday 2026-07-24 — Chris Pilon + Pilar
Group | Items | Days | Status / Blocker
Foundation | 1. SQLite→Postgres (incl. 1a Graph perf + 1b Pagination) | 8 days | First item — performance foundation
Architecture Layers | 2. Staging · 3. Integration · 4. Access Layer | 16 days | Jon Brightling architecture (2026-07-17)
Additional scope | 5–10. Runtime, Lineage, AI, Ref data, Incremental, Timestamps | 20 days | Item 8 blocked on extractor change
Buffer | 11. Contingency | 5 days | Reserved for unanticipated items
TOTAL NET |  | ~39 days | ~6 weeks with AI-assisted development
Sub-tasks 1a (Graph engine perf) and 1b (Frontend pagination) are included within item 1 total and are not double-counted in the net total.